Disclaimer: This is the BEAD Pre-Construction NEPA and Permitting Timeline Version 3, published on April 6th, 2026.  The Wisconsin Broadband Office reserves the right to modify or update this document as necessary to effectuate the goals of the BEAD program and remain compliant with State, Federal or NTIA requirements or for any other reason to administer the BEAD program.

Pre-Construction NEPA and Permitting Timeline

Subgrantees must provide a “milestone schedule” (which will be called “Pre-Construction NEPA and Permitting Timeline”, to not be confused with the milestone schedule tied to the BEAD milestone payments detailed in the Grant Agreement) to initiate National Environmental Policy Act (NEPA) Review by the National Telecommunications and Information Administration (NTIA). This Pre-Construction NEPA and Permitting Timeline must identify specific deadlines and describing how the Subgrantee proposes to meet timing requirements including, as required, the completion of consultations, the completion of NEPA and Section 106 reviews, and the submission of Environmental Assessments (EAs) or Environmental Impact Statements (EISs). The Pre-Construction NEPA and Permitting Timeline will be included and submitted with a required project deployment plan following Grant Agreement execution between the Subgrantee and the PSC.

In the table below, fill out the “anticipated completion of milestone” column for each row. Add notes where it would be useful for Public Service Commission (PSC) staff. One Timeline shall be completed for each project. If a subrecipient has NEPA Sub-Projects, then one Timeline shall be completed for each NEPA Sub-Project. Note that it’s possible for milestones to be completed concurrently. Some cells have been pre-filled for convenience.

If you anticipate your project falling into a Categorical Exclusion (CatEx), NEPA should take 3-6 months. Environmental Analyses will take longer. Most BEAD projects will be Categorical Exclusions.

Submit this document as part of your larger project deployment schedule to the Grants Management System as document type “Onboarding Document”. As staff availability allows, PSC staff will complete Section 106 and Section 7 Consultations on behalf of the Subgrantee.

Subgrantee Name:

Project Name and ID:

[If Applicable] NEPA Sub-Project ID:

Short Project Description:

| Milestone | Anticipated Start of Milestone | # Days Anticipated to Complete | Notes |
| --- | --- | --- | --- |
| PSC announces preliminary awards and submits Final Proposal to NTIA | September 4 2025 | 0 | Completed |
| Certified Engineering plan submitted to PSC |  | <90 |  |
| NTIA approval of Wisconsin’s Final Proposal | December 2 2025 | 90 | Completed |
| Tribal consent received |  |  |  |
| Grant Agreement signed |  | 30-60 | Following NTIA approval of awards, submission of required docs, tribal consent |
| NEPA Review |  |  |  |
| Subgrantee submits Environmental Impacts and Documentation Screening Questionnaire and all other requested materials to the PSC |  | 30-60 |  |
| Section 7 Consultation completed |  | 30-135 |  |
| Section 106 Consultation completed |  | >30 |  |
| [If Applicable] Section 106 Interested Tribe Consultation(s) Completed |  |  |  |
| NEPA level (CatEx, EA, EIS) determined |  |  |  |
| Subgrantee has received NEPA Decision Document, notified of NEPA approval, and is authorized to begin implementation |  |  |  |
| [If Applicable] Permitting |  |  |  |
| Pre-application meetings with permitting agencies |  | <30 |  |
| Permit applications submitted to permitting agencies |  | 30-60 |  |
| Permit applications determined complete by permitting agencies |  |  |  |
| Permitting agency review time |  |  |  |
| Subgrantee provides proof that all required permits have been applied for |  |  |  |
| Project Construction begins |  |  |  |
| Permitting Agencies: |  |  |  |

Provide a brief narrative to describe the completion of the consultations, NEPA and Section 106 reviews, and submission of NEPA documentation:

[If Applicable] Provide a brief narrative to describe how the Pre-Construction NEPA and Permitting Timeline differs between NEPA Sub-Projects: